## Tracker
Module | Activity Name | Unique Code | Related DB Entities | Dependencies | Priority/Sprint
DATA | Connection Manager | DATA-00-001 | system_config, trusts, system_users, migration_versions, sessions, system_audit_logs, schools, classes, sections, users, user_school_assignments, houses, academic_years, trust_config, audit_logs |  | 0
DATA | Master DB schema creation | DATA-00-002 | system_config, trusts, system_users, migration_versions, sessions, system_audit_logs |  | 0
DATA | Trust DB schema template | DATA-00-003 | schools, classes, sections, users, user_school_assignments, houses, academic_years, trust_config, audit_logs | DATA-00-002 | 0
DATA | System config storage | DATA-00-004 | system_config | DATA-00-002 | 0
DATA | Trust registry & subdomains | DATA-00-005 | trusts | DATA-00-002 | 0
DATA | System users (sys/group admin) | DATA-00-006 | system_users | DATA-00-002 | 0
DATA | Migration tracking | DATA-00-007 | migration_versions | DATA-00-002, DATA-00-005 | 0
DATA | Session store | DATA-00-008 | sessions | DATA-00-002 | 0
DATA | Global audit logging | DATA-00-009 | system_audit_logs | DATA-00-002 | 0
DATA | Tenant audit logging | DATA-00-010 | audit_logs | DATA-00-003 | 0
DATA | Subdomain/config cache | DATA-00-011 | trusts, system_config | DATA-00-004, DATA-00-005 | 0
DATA | Pool cleanup & housekeeping | DATA-00-012 |  | DATA-00-001 | 0
SETUP | Wizard: Trust creation | SETUP-01-001 | trusts, system_config | DATA-* | 1
SETUP | Wizard: School creation | SETUP-01-002 | schools | DATA-*, SETUP-01-001 | 1
SETUP | Wizard: Academic year creation | SETUP-01-003 | academic_years | SETUP-01-002 | 1
SETUP | Class & section setup (+ House) | SETUP-01-004 | classes, sections, houses | SETUP-01-003 | 1
SETUP | Subject & grading configuration | SETUP-01-005 | classes, trust_config | SETUP-01-004 | 1
SETUP | Trust/school-level config | SETUP-01-006 | trust_config | SETUP-01-002 | 1
SETUP | Role seeding (admins) | SETUP-01-007 | users, trust_config | SETUP-01-002 | 1
AUTH | Local authentication (web sessions) | AUTH-02-001 | users, sessions, audit_logs | DATA-*, SETUP-01-007 | 2
AUTH | JWT authentication (APIs) | AUTH-02-002 | users, audit_logs | AUTH-02-001 | 2
AUTH | Multi-factor (OTP) | AUTH-02-003 | users, audit_logs, trust_config | AUTH-02-001 | 2
AUTH | RBAC (roles & permissions) | AUTH-02-004 | users, trust_config | SETUP-01-007 | 2
AUTH | Permission mapping | AUTH-02-005 | trust_config | AUTH-02-004 | 2
AUTH | Account lockout | AUTH-02-006 | users, audit_logs | AUTH-02-001 | 2
AUTH | Email/phone verification | AUTH-02-007 | users, audit_logs | AUTH-02-001 | 2
AUTH | Password reset flows | AUTH-02-008 | users, audit_logs, system_audit_logs | AUTH-02-001 | 2
AUTH | Auth event logging | AUTH-02-009 | audit_logs, system_audit_logs | AUTH-02-001 | 2
AUTH | API keys/tokens | AUTH-02-010 | trust_config, users | AUTH-02-002 | 2
USER | User creation & management | USER-03-001 | users, schools | SETUP-01-002, AUTH-* | 3
USER | User-school assignments | USER-03-002 | user_school_assignments, users, schools | USER-03-001 | 3
USER | Role & permission assignment | USER-03-003 | users, trust_config | AUTH-02-004 | 3
USER | Teacher subject/class allocation | USER-03-004 | users, classes, sections, trust_config | SETUP-01-004, USER-03-001 | 3
USER | Staff profile management | USER-03-005 | users | USER-03-001 | 3
USER | Parent-student linking | USER-03-006 | users, student_parents, students | STUD-04-001 | 3
STUD | Student admission | STUD-04-001 | students, admissions, documents | SETUP-*, AUTH-* | 4
STUD | Admission approval workflow | STUD-04-002 | admissions, audit_logs | STUD-04-001 | 4
STUD | Readmission/promotion | STUD-04-003 | students, academic_years, sections | SETUP-01-003, SETUP-01-004 | 4
STUD | Inter-school transfer (in-trust) | STUD-04-004 | student_transfers, schools, students | STUD-04-001, SETUP-01-002 | 4
STUD | Student ID & roll allocation | STUD-04-005 | students, sections | STUD-04-001, SETUP-01-004 | 4
STUD | Siblings & category allocation | STUD-04-006 | students, student_parents, trust_config | STUD-04-001 | 4
STUD | Student documents & certificates | STUD-04-007 | documents, students | STUD-04-001 | 4
FEES | Fee heads & structures | FEES-05-001 | fee_heads, fee_structures, fee_installments | SETUP-* | 5
FEES | Class & student fee mapping | FEES-05-002 | student_fee_assignments, fee_structures | FEES-05-001, STUD-04-001 | 5
FEES | Discount allocation | FEES-05-003 | student_fee_assignments, trust_config | FEES-05-002 | 5
FEES | Transport/optional services | FEES-05-004 | trust_config, student_fee_assignments | FEES-05-002 | 5
FEES | Late fee rules (config/override) | FEES-05-005 | trust_config, student_fee_assignments | SETUP-01-006, FEES-05-002 | 5
FEES | Fee collection & receipts | FEES-05-006 | fee_receipts, student_fee_assignments | FEES-05-002 | 5
FEES | Payment gateway integration | FEES-05-007 | payment_gateway_logs, fee_receipts | FEES-05-006 | 5
FEES | Refunds & adjustments | FEES-05-008 | fee_receipts | FEES-05-006 | 5
FEES | Reports, reconciliation & defaulters | FEES-05-009 | fee_receipts, student_fee_assignments | FEES-05-006 | 5
ATTD | Daily attendance & bulk import | ATTD-06-001 | attendance_daily, attendance_summary | SETUP-01-004, STUD-* | 6
ATTD | Leave/absence workflows | ATTD-06-002 | attendance_daily, trust_config | ATTD-06-001 | 6
ATTD | Attendance reporting/analytics | ATTD-06-003 | attendance_summary | ATTD-06-001 | 6
REPT | Student profile reports | REPT-07-001 | students, admissions | STUD-* | 7
REPT | Fee collection reports | REPT-07-002 | fee_receipts, student_fee_assignments | FEES-* | 7
REPT | Attendance summary reports | REPT-07-003 | attendance_summary, students | ATTD-* | 7
REPT | Academic performance reports | REPT-07-004 | classes, sections, trust_config | SETUP-* | 7
REPT | Custom report builder | REPT-07-005 | reports, report_templates | DATA-*, SETUP-* | 7
REPT | Export to PDF/Excel | REPT-07-006 | reports | REPT-07-001, REPT-07-002, REPT-07-003 | 7
DASH | Trust admin dashboard | DASH-08-001 | schools, users, fee_receipts, attendance_summary | DATA-*, SETUP-*, FEES-*, ATTD-* | 8
DASH | School admin dashboard | DASH-08-002 | users, students, fee_receipts, attendance_summary | SETUP-*, FEES-*, ATTD-* | 8
DASH | Teacher dashboard | DASH-08-003 | classes, sections, attendance_daily | SETUP-*, ATTD-* | 8
COMM | Notifications (SMS/Email/WhatsApp) | COMM-09-001 | communication_templates, communication_messages | USER-*, STUD-*, FEES-* | 9
COMM | In-app announcements | COMM-09-002 | communication_templates, communication_campaigns | USER-* | 9
COMM | Emergency alerts (broadcast) | COMM-09-003 | communication_templates, communication_campaigns, communication_messages | USER-*, STUD-* | 9