## Sheet1
Module | Activity Name | Unique Code | Related DB Entities | Dependencies | Priority/Sprint | Acceptance Criteria | Test Data Requirements | API Endpoints
DATA | Connection Manager | DATA-00-001 | system_config, trusts, system_users, migration_versions, sessions, system_audit_logs, schools, classes, sections, users, user_school_assignments, houses, academic_years, trust_config, audit_logs |  | 0 | Verify that 'Connection Manager' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Connection Manager, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Master DB schema creation | DATA-00-002 | system_config, trusts, system_users, migration_versions, sessions, system_audit_logs |  | 0 | Verify that 'Master DB schema creation' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Master DB schema creation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Trust DB schema template | DATA-00-003 | schools, classes, sections, users, user_school_assignments, houses, academic_years, trust_config, audit_logs | DATA-00-002 | 0 | Verify that 'Trust DB schema template' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Trust DB schema template, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | System config storage | DATA-00-004 | system_config | DATA-00-002 | 0 | Verify that 'System config storage' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for System config storage, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Trust registry & subdomains | DATA-00-005 | trusts | DATA-00-002 | 0 | Verify that 'Trust registry & subdomains' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Trust registry & subdomains, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | System users (sys/group admin) | DATA-00-006 | system_users | DATA-00-002 | 0 | Verify that 'System users (sys/group admin)' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for System users (sys/group admin), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Migration tracking | DATA-00-007 | migration_versions | DATA-00-002, DATA-00-005 | 0 | Verify that 'Migration tracking' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Migration tracking, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Session store | DATA-00-008 | sessions | DATA-00-002 | 0 | Verify that 'Session store' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Session store, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Global audit logging | DATA-00-009 | system_audit_logs | DATA-00-002 | 0 | Verify that 'Global audit logging' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Global audit logging, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Tenant audit logging | DATA-00-010 | audit_logs | DATA-00-003 | 0 | Verify that 'Tenant audit logging' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Tenant audit logging, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Subdomain/config cache | DATA-00-011 | trusts, system_config | DATA-00-004, DATA-00-005 | 0 | Verify that 'Subdomain/config cache' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Subdomain/config cache, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DATA | Pool cleanup & housekeeping | DATA-00-012 |  | DATA-00-001 | 0 | Verify that 'Pool cleanup & housekeeping' in module 'DATA' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Pool cleanup & housekeeping, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/data/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Wizard: Trust creation | SETUP-01-001 | trusts, system_config | DATA-* | 1 | Verify that 'Wizard: Trust creation' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Wizard: Trust creation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Wizard: School creation | SETUP-01-002 | schools | DATA-*, SETUP-01-001 | 1 | Verify that 'Wizard: School creation' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Wizard: School creation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Wizard: Academic year creation | SETUP-01-003 | academic_years | SETUP-01-002 | 1 | Verify that 'Wizard: Academic year creation' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Wizard: Academic year creation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Class & section setup (+ House) | SETUP-01-004 | classes, sections, houses | SETUP-01-003 | 1 | Verify that 'Class & section setup (+ House)' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Class & section setup (+ House), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Subject & grading configuration | SETUP-01-005 | classes, trust_config | SETUP-01-004 | 1 | Verify that 'Subject & grading configuration' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Subject & grading configuration, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Trust/school-level config | SETUP-01-006 | trust_config | SETUP-01-002 | 1 | Verify that 'Trust/school-level config' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Trust/school-level config, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
SETUP | Role seeding (admins) | SETUP-01-007 | users, trust_config | SETUP-01-002 | 1 | Verify that 'Role seeding (admins)' in module 'SETUP' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Role seeding (admins), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/setup/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Local authentication (web sessions) | AUTH-02-001 | users, sessions, audit_logs | DATA-*, SETUP-01-007 | 2 | Verify that 'Local authentication (web sessions)' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Local authentication (web sessions), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | JWT authentication (APIs) | AUTH-02-002 | users, audit_logs | AUTH-02-001 | 2 | Verify that 'JWT authentication (APIs)' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for JWT authentication (APIs), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Multi-factor (OTP) | AUTH-02-003 | users, audit_logs, trust_config | AUTH-02-001 | 2 | Verify that 'Multi-factor (OTP)' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Multi-factor (OTP), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | RBAC (roles & permissions) | AUTH-02-004 | users, trust_config | SETUP-01-007 | 2 | Verify that 'RBAC (roles & permissions)' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for RBAC (roles & permissions), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Permission mapping | AUTH-02-005 | trust_config | AUTH-02-004 | 2 | Verify that 'Permission mapping' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Permission mapping, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Account lockout | AUTH-02-006 | users, audit_logs | AUTH-02-001 | 2 | Verify that 'Account lockout' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Account lockout, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Email/phone verification | AUTH-02-007 | users, audit_logs | AUTH-02-001 | 2 | Verify that 'Email/phone verification' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Email/phone verification, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Password reset flows | AUTH-02-008 | users, audit_logs, system_audit_logs | AUTH-02-001 | 2 | Verify that 'Password reset flows' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Password reset flows, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | Auth event logging | AUTH-02-009 | audit_logs, system_audit_logs | AUTH-02-001 | 2 | Verify that 'Auth event logging' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Auth event logging, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
AUTH | API keys/tokens | AUTH-02-010 | trust_config, users | AUTH-02-002 | 2 | Verify that 'API keys/tokens' in module 'AUTH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for API keys/tokens, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/auth/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | User creation & management | USER-03-001 | users, schools | SETUP-01-002, AUTH-* | 3 | Verify that 'User creation & management' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for User creation & management, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | User-school assignments | USER-03-002 | user_school_assignments, users, schools | USER-03-001 | 3 | Verify that 'User-school assignments' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for User-school assignments, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | Role & permission assignment | USER-03-003 | users, trust_config | AUTH-02-004 | 3 | Verify that 'Role & permission assignment' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Role & permission assignment, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | Teacher subject/class allocation | USER-03-004 | users, classes, sections, trust_config | SETUP-01-004, USER-03-001 | 3 | Verify that 'Teacher subject/class allocation' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Teacher subject/class allocation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | Staff profile management | USER-03-005 | users | USER-03-001 | 3 | Verify that 'Staff profile management' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Staff profile management, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
USER | Parent-student linking | USER-03-006 | users, student_parents, students | STUD-04-001 | 3 | Verify that 'Parent-student linking' in module 'USER' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Parent-student linking, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/user/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Student admission | STUD-04-001 | students, admissions, documents | SETUP-*, AUTH-* | 4 | Verify that 'Student admission' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Student admission, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Admission approval workflow | STUD-04-002 | admissions, audit_logs | STUD-04-001 | 4 | Verify that 'Admission approval workflow' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Admission approval workflow, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Readmission/promotion | STUD-04-003 | students, academic_years, sections | SETUP-01-003, SETUP-01-004 | 4 | Verify that 'Readmission/promotion' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Readmission/promotion, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Inter-school transfer (in-trust) | STUD-04-004 | student_transfers, schools, students | STUD-04-001, SETUP-01-002 | 4 | Verify that 'Inter-school transfer (in-trust)' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Inter-school transfer (in-trust), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Student ID & roll allocation | STUD-04-005 | students, sections | STUD-04-001, SETUP-01-004 | 4 | Verify that 'Student ID & roll allocation' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Student ID & roll allocation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Siblings & category allocation | STUD-04-006 | students, student_parents, trust_config | STUD-04-001 | 4 | Verify that 'Siblings & category allocation' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Siblings & category allocation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
STUD | Student documents & certificates | STUD-04-007 | documents, students | STUD-04-001 | 4 | Verify that 'Student documents & certificates' in module 'STUD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Student documents & certificates, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/stud/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Fee heads & structures | FEES-05-001 | fee_heads, fee_structures, fee_installments | SETUP-* | 5 | Verify that 'Fee heads & structures' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Fee heads & structures, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Class & student fee mapping | FEES-05-002 | student_fee_assignments, fee_structures | FEES-05-001, STUD-04-001 | 5 | Verify that 'Class & student fee mapping' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Class & student fee mapping, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Discount allocation | FEES-05-003 | student_fee_assignments, trust_config | FEES-05-002 | 5 | Verify that 'Discount allocation' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Discount allocation, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Transport/optional services | FEES-05-004 | trust_config, student_fee_assignments | FEES-05-002 | 5 | Verify that 'Transport/optional services' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Transport/optional services, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Late fee rules (config/override) | FEES-05-005 | trust_config, student_fee_assignments | SETUP-01-006, FEES-05-002 | 5 | Verify that 'Late fee rules (config/override)' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Late fee rules (config/override), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Fee collection & receipts | FEES-05-006 | fee_receipts, student_fee_assignments | FEES-05-002 | 5 | Verify that 'Fee collection & receipts' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Fee collection & receipts, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Payment gateway integration | FEES-05-007 | payment_gateway_logs, fee_receipts | FEES-05-006 | 5 | Verify that 'Payment gateway integration' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Payment gateway integration, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Refunds & adjustments | FEES-05-008 | fee_receipts | FEES-05-006 | 5 | Verify that 'Refunds & adjustments' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Refunds & adjustments, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
FEES | Reports, reconciliation & defaulters | FEES-05-009 | fee_receipts, student_fee_assignments | FEES-05-006 | 5 | Verify that 'Reports, reconciliation & defaulters' in module 'FEES' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Reports, reconciliation & defaulters, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/fees/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
ATTD | Daily attendance & bulk import | ATTD-06-001 | attendance_daily, attendance_summary | SETUP-01-004, STUD-* | 6 | Verify that 'Daily attendance & bulk import' in module 'ATTD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Daily attendance & bulk import, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/attd/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
ATTD | Leave/absence workflows | ATTD-06-002 | attendance_daily, trust_config | ATTD-06-001 | 6 | Verify that 'Leave/absence workflows' in module 'ATTD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Leave/absence workflows, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/attd/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
ATTD | Attendance reporting/analytics | ATTD-06-003 | attendance_summary | ATTD-06-001 | 6 | Verify that 'Attendance reporting/analytics' in module 'ATTD' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Attendance reporting/analytics, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/attd/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Student profile reports | REPT-07-001 | students, admissions | STUD-* | 7 | Verify that 'Student profile reports' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Student profile reports, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Fee collection reports | REPT-07-002 | fee_receipts, student_fee_assignments | FEES-* | 7 | Verify that 'Fee collection reports' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Fee collection reports, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Attendance summary reports | REPT-07-003 | attendance_summary, students | ATTD-* | 7 | Verify that 'Attendance summary reports' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Attendance summary reports, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Academic performance reports | REPT-07-004 | classes, sections, trust_config | SETUP-* | 7 | Verify that 'Academic performance reports' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Academic performance reports, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Custom report builder | REPT-07-005 | reports, report_templates | DATA-*, SETUP-* | 7 | Verify that 'Custom report builder' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Custom report builder, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
REPT | Export to PDF/Excel | REPT-07-006 | reports | REPT-07-001, REPT-07-002, REPT-07-003 | 7 | Verify that 'Export to PDF/Excel' in module 'REPT' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Export to PDF/Excel, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/rept/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DASH | Trust admin dashboard | DASH-08-001 | schools, users, fee_receipts, attendance_summary | DATA-*, SETUP-*, FEES-*, ATTD-* | 8 | Verify that 'Trust admin dashboard' in module 'DASH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Trust admin dashboard, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/dash/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DASH | School admin dashboard | DASH-08-002 | users, students, fee_receipts, attendance_summary | SETUP-*, FEES-*, ATTD-* | 8 | Verify that 'School admin dashboard' in module 'DASH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for School admin dashboard, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/dash/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
DASH | Teacher dashboard | DASH-08-003 | classes, sections, attendance_daily | SETUP-*, ATTD-* | 8 | Verify that 'Teacher dashboard' in module 'DASH' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Teacher dashboard, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/dash/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
COMM | Notifications (SMS/Email/WhatsApp) | COMM-09-001 | communication_templates, communication_messages | USER-*, STUD-*, FEES-* | 9 | Verify that 'Notifications (SMS/Email/WhatsApp)' in module 'COMM' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Notifications (SMS/Email/WhatsApp), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/comm/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
COMM | In-app announcements | COMM-09-002 | communication_templates, communication_campaigns | USER-* | 9 | Verify that 'In-app announcements' in module 'COMM' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for In-app announcements, covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/comm/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec
COMM | Emergency alerts (broadcast) | COMM-09-003 | communication_templates, communication_campaigns, communication_messages | USER-*, STUD-* | 9 | Verify that 'Emergency alerts (broadcast)' in module 'COMM' meets functional and non-functional requirements, passes unit & integration tests, and adheres to security & RBAC rules. | Prepare mock data for Emergency alerts (broadcast), covering valid, invalid, and edge cases; include role-based access scenarios. | /api/v1/comm/<resource> (GET/POST/PUT/DELETE) — exact routes per detailed spec